## Slide 1: Monitoring evaluation and learning (MEL)

## Slide 2: Monitoring and evaluation of what?
Sphere of control = operational environment
Direct control
Programme
Sphere of influence = relationships & interactions
Direct influence
Actor groups/ Boundary partners
Sphere of interest
= social, economical, environmental factors
Indirect influence / Contribution
Stakeholders / beneficiaries
Inputs
Activities/ strategies
Outputs
Outcomes
Impacts
Auto-monitoring, MtR
Ootcome Mapping
impact evaluations
Ooutcome Harvesting + stories/sensemaking

## Slide 3: Systematic result analysis, monitoring evaluation, learning and reporting
Participative processes
From planning to evaluation
Important to differentiate between
  1. WHAT YOU DO (activities, strategies)
  2. WHAT YOU ACHIEVE (outputs, outcomes, indicators, targets)
  3. HOW CONTEXT affects the result (assumptions and risks)

## Slide 4: What is MEL? Monitoring
Monitoring can be explained as:
A routine to collect and analyse information to track progress against what you had planned.
Monitoring helps you in detecting trends and patterns, helps you to adapt your work, to take informed decisions in your project management. There are different types of monitoring.
Organizational monitoring
Performance monitoring
Process (activity) monitoring
Results monitoring
Effective monitoring helps you to know if the intended results are achieved, what you may need to do differently to get the results you are aiming at.
Notes: The material to this slide can be found in the partner guideline annex with explaination of key RBM concepts (Annex 6)
Organizational monitoring tracks the sustainability, institutional development and capacity building in the project/programme and with its partners.
Performance monitoring is a continuous process of collecting and analysing data in order to compare how well a project, program, or policy is being implemented in relation to expected results.
Process (activity) monitoring tracks the use of resources, the progress of activities and the delivery of results. It examines how activities are delivered in terms of efficient use of time and resources.
Results monitoring tracks the effects and impacts. It determines any progress towards the intended objectives and whether there may be any unintended impact, positive or negative.

## Slide 5: What is MEL? Evaluation
Evaluation can be explained as:
An assessment that identifies, reflects upon and to the extent possible check the real worth of the project’s effects.
It should be as systematic and as objective as possible. It can be done on ongoing or completed projects, including on how well the project was designed implementation and what results the project has/had.
There is a sea of different evaluations – for the MEL, these are key:
Internal or self- evaluation
Midterm evaluation
Impact evaluation
Notes: The material to this slide can be found in the partner guideline annex with explaination of key RBM concepts (Annex 6)
The aim is to determine the relevance and fulfilment of objectives, developmental efficiency, effectiveness, impact and sustainability. An evaluation should provide information that is credible and useful, enabling the incorporation of lessons learned into the decision-making process of both recipients and donors.” (OECD/DAC 2002).
Internal or self- evaluation is conducted by those responsible for implementing a project or programme. It is typically more participatory and reinforces ownership and understanding among the project or programme team.
Midterm evaluation is a formative evaluation that occurs midway through implementation.
Impact evaluation focuses on the effect of a project or programme, rather than on its management and delivery. Therefore, an impact evaluation typically occurs after the completion
Explanation of other types:
There are different types of evaluation. Ex-ante evaluation is performed before implementation of a development intervention. Related terms: appraisal, quality at entry. Ex- post evaluations are conducted sometime after implementation to assess long-term impact and sustainability. External or independent evaluation is conducted by evaluators outside of the implementing project or programme team, lending it a degree of objectivity and often technical expertise. Final evaluation is a summative evaluation conducted (often externally) at the completion of project or programme in order to assess how well the project or programme achieved its intended objectives. Formative evaluations occur during project or programme implementation to improve performance and assess compliance. Internal or self- evaluation is conducted by those responsible for implementing a project or programme. It is typically more participatory and reinforces ownership and understanding among the project or programme team. Impact evaluation focuses on the effect of a project or programme, rather than on its management and delivery. Therefore, an impact evaluation typically occurs after the completion of a project or programme, during a final evaluation or an ex-post evaluation. Joint evaluation is conducted collaboratively by more than one implementing partner, and can help build consensus at different levels, credibility and joint support. Meta-evaluation is used to assess the evaluation process itself. Examples include an inventory of evaluations to inform the selection of future evaluations; the synthesis of evaluation results; checking compliance with evaluation policy and good practices; assessing how well evaluations are disseminated and utilized for organizational learning and change, etc. Midterm evaluation is a formative evaluation that occurs midway through implementation.

## Slide 6: What is MEL? Learning
Learning can be explained as:
A deeper understanding of consequences/effects that a specific situation/context led to (which your project contributed to in a good or bad manner) – a knowledge you can then apply in a a more broad sense.
E.g. in one community a more diverse set of people were engaged in the demarcation process, by first letting 1. women, 2. young women and men 3. men work in own separate groups, compare results and reach consensus on the material – we then decided to make use of this methodology also for other types of engagement. This is a methodological learning you can integrate in your monitoring approach!
You have learned something for real only when you implement what you learned. E.g. changing behaviour. If you know you should do something differently, but continue doing the same as before, no real learning has taken place.
Notes: The material to this slide can be found in the partner guideline annex with explaination of key RBM concepts (Annex 6)
Ask you partner what kind of things they have learned recently which affected how they are working? They will have various stories to share.
You can here advice that they have ‘structured learning’ - creating meetings where this kind of learning is systemtically being embedded into the organisation, staff and managers (as well as being recorded so the learning can be reported and learning shared beyond their own organistion)

## Slide 7: What is MEL? Reporting
Reporting can be explained as:
A process to provide analysed data such as information from communities and other key stakeholders.
Internal reporting
External reporting
Notes: The material to this slide can be found in the partner guideline annex with explaination of key concepts (Annex 6)
In the MEL Partner Guide, partners have access to a set of questions which a reporting should include (Annex 4)
Internal reporting is conducted for actual project/programme implementation. It plays a crucial role in lesson learning to facilitate decision-making and ultimately, it indicates what can be extracted and reported externally.
External reporting is conducted to inform stakeholders outside the project/programme team and implementing organization, and is important for accountability.

## Slide 8: Why engage in a MEL process ?
So you can grow by…
Creating conditions so staff, managers and external stakeholders feel comfortable in sharing good and bad experiences
Creating structures so you learn from results/changes you achieve or contribute to and changes which affect you
Creating structures so you can adapt your project and organisation in accordance with what you learned
Notes: Potentially you ask participants about WHY they think they should engage in a MEL process, before you provide your explanation.

## Slide 9: What do we mean by a MEL process?
The MEL is a process because you take steps to build the work, to learn, to adjust on a continuous basis. It is something which grows within the organisation, forms the organisation and affect how you work over time.
Consequently MEL is also something which grows in your staff, in your management and in the people you engage with.
Some fundamental aspects of the MEL process are:
Notes: Potentially you ask participants WHAT they mean by a MEL process, before you provide your explanation.

## Slide 10: Monitoring process and planning
Monitoring process:
Establishing a baseline: what exist before the intervention?
Planning the monitoring within the frame of analysis of results
Develop mechanisms to measure effects/impacts and analysis of results during the entire project cycle
Allocation of resources: human, financial, timewise
Monitoring plan:
Indicators (what you will measure
Methods (how you will collect data
Where (location of data collection
When (timeframe and frequency of data collection)
who (people responsible for data collection)
Who will analyse and use the data
Cost of monitoring these indicators
Baseline data (measurement and date
Final desired result (target)

## Slide 11: Monitoring planing matrix
Results level | What? Indicator | How? Methods | Where? | When? | Who? Responsible for data collection | Who? Responsible for analysis and use the data | Cost | Baseline Data | Target
Outcome 1 |  |  |  |  |  |  |  |  | 
Output |  |  |  |  |  |  |  |  | 
Output |  |  |  |  |  |  |  |  | 
Outcome 2 |  |  |  |  |  |  |  |  | 
Output |  |  |  |  |  |  |  |  | 
Output |  |  |  |  |  |  |  |  | 

## Slide 12: MEL and project Cycle

## Slide 13
INDICATORS

## Slide 14: What is an indicator?
An indicator is something that helps you understand where you are, which way you are going and how far you are from where you want to be.
A good indicator alerts you to a problem before it gets too bad and helps you recognize what needs to be done to fix the problem
Each indicators will have baseline information (value of the indicators in the beginning of the project) and target: the expected value of the indicator at the end of the project.
Example:
Indicator: # of women who increase knowledge about their rights, base line: # of women who have knowledge about their rights in the beginning of the project (20%) Target: at least 95 % of women trained increase their knowledge about their rights.
()
Notes: M

## Slide 15: Indicators - definition
Indicators
  measure whether results have been achieved
  can be qualitative or quantitative
  do not change over time and
  should be neutral and integrated in the project process
  help decision makers make relevant decisions, negotiate and communicate
  illustrate the cause and effect relationships between inputs and results
Notes: M
If for some reason you need to send someone else to check on your results, what should they look for, where and why?

## Slide 16: Indicators – Following the result chain
Input: Resources (human/financial)
            ex. number of educators
Activities Activities implemented
            ex. number of sessions and trained people
Output Short-term result/effect of activity
            ex. level of competence of persons trained and quality of training
Notes: M

## Slide 17: Result indicators
Short, Mid-term Outcomes: results and effects, Measure changes. Indicators are quantitative or qualitative
                ex. Applied knowledge
                ex. change on organizational level
Impact Long-term results. Related to overall objectives and development goals
                ex. change on institutional or national level

## Slide 18: Quantitative & Qualitative
How many?
How often?
How much?
How?
When?
Who?
Where?
What?
Why?

## Slide 19: Purely quantitative
XX women participates in workshops
X number of meetings per month
XX courses implemented

## Slide 20: Indicators: quantitative/qualitative
XX number of journalists trained twice a week in HR reporting (gender, age, ethnicity, geography etc)
XX number of women actively participating in local political entities and the level of participation (has to be defined)
% young people (gender, age, ethnicity, geography etc) getting work in region XX 1 year after completed project.

## Slide 21
Some method used in planning, monitoring and evaluation

## Slide 22: Theory of Change
Seek to explain what we expect to happen in our work
Seek to explain and make visible the assumptions we make on how the goals/results are linked
Seek to explain the ’missing middle’ (OM also has this focus)
Works from ’desired goal’ backwards – ask: what conditions must be in place (causal thinking as LFA)
Participatory process (as LFA and OM)
Good step for developing a logframe á la LFA

## Slide 23: LFA
Stakeholder analysis
Contextual analysis/Problem analysis – solutions
Risk analysis
Works for some projects/organisations when participatory and is more than the log frame
Risks/limitations: Too focused on outputs, instead of change, linear thinking, Counting, tendency to focus on attribution

## Slide 24: Outcome Mapping
Focus on outcomes as changes in behavior/attitudes
Focus on boundary partners
OM-instruments not difficult to understand, but demand a cultural shift in organisations as it demands that organisations MONITORS outcomes – monitoring is sometimes not taking place, is inadequate or is focusing on reporting.
Risk/limitations: Links to national level indicators can be weak, clear baselines needed, becoming too subjective! Forget the outputs needed to reach outcomes?

## Slide 25: An outcome for OM/OH?
Not about what you did!
It is about who changed because of what you did!

## Slide 26: Outcome Harvesting
Originally an evaluation tool
What is new?
Identify relevant changes in relevant actors … then backtrack this to the activities of the project.
Demands engagement at another level – which may lead to higher learning!
Risks/limitattions: comprehensive and therefore resource heavy.