## Slide 1: A result oriented organization

## Slide 2: External factors: assumptions and risks, chapter 7 (LFA step 8 and 9). PR1
The analysis of external factors will lead to three types of interventions:
      Adaption of the intervention logic, by adding results or activities
      B. Increasing the external factors or prerequisites
      Searching for further information to deepen the knowledge about the planned efforts.
      Program abandonment

## Slide 3: Assumptions
Situations, things that occur, or decisions that need to be taken, that occur, for the success of the project, but that are partly or completely out of the projects control.
They are also known as conditions or hypothesis.
To establish assumptions helps to:
- look over risks and possibilities for success
avoid the risks, by reformulating the project
- limit area and responsibility for the responsible of the project- show areas where more information or research might be needed

## Slide 4: Risks
Situations, things that occur or decisions taken that are mainly or completely outside the programme’s control and that imply a threat for the future intervention.
Analysis of the risks help to
- Identify possibilities for success
- Avoid great risks, by reformulating the programme
- Limit area and responsibility for the responsible of the programme
- Show areas where more information or research might be necessary
- Identification of some ” killing factors” and reformulation of the entire programme or parts of it.

## Slide 5: Risk management
 |  |  | Risk Analysis and Risk Management |  | 
Risks | Probability (1-5) | Consequence (1-5) | Risk factor (probability x consequence) | Strategy: Risk Mitigation / Management | Risk related to objective number
1. |  |  |  |  | 
2. |  |  |  |  | 
3. |  |  |  |  | 
4. |  |  |  |  | 
5. |  |  |  |  | 
6. |  |  |  |  | 
7. |  |  |  |  |