## Slide 1
Stakeholders analysis

## Slide 2: Stakeholders are
Target groups.
Actors (Project team, decissions makers)
Allies/antagonist

## Slide 3: Target groups
Target groups are Primary/Final/right holders or Secondary/intermediaries
Example of primary target groups: population at large, marginalized women and men, youth, children, girls, etc.
Example of secondary target groups
partners of cooperation, other actors we direct our efforts to, staff, teachers, (if children are the primary target group)

## Slide 4: More about target groups
The primary target group can be indirect, we don’t work directly towards them – (instead - partners of cooperation, staff, teacher etc. do work directly).
The secondary target group is however often direct.
In the secondary target group we can measure effects - but all effects need to be related to achieving changes (effects) in the primary target group.

## Slide 5: The actors
They are the people or entities responsable for the design, implementation, monitoring and reporting of the Project
In this category of stakeholders we indetify:
Project group, bord, executive comité,coordinators structure, management structures, implementing teams etc

## Slide 6: The allies/antagonist
In this category of stakeholders we identify the groups, organisations, persons who are not implementing the Project but:
they support the Project (allies)
act against the Project(antagonist)

## Slide 7: Analysis of target groups Identify the groups or persons in this category and analyse the strengths and weakness for each of them
Group: primary/secondary | Strengths | Weaknesses

## Slide 8: Analysis of actors Identify the groups or persons in this category and analyse the strengths, weaknesses, problems and interests/motivation for each of them
Group | Strengths | Weaknesses | Problems
Interests/Motivation

## Slide 9: Analysis of allies/antagonists
Group | Interests | Possibilities | Threats
Identify the groups or persons in this category and analyse the interests, possibilities and threats for each of them