## Slide 1: Result based Management

## Slide 2: RBM Approach for planning, monitoring and evaluation of results

## Slide 3: Results (OECD Glossary)
The output, outcome or impact
(intended or unintended, positive and/or negative) of a development intervention.
Related terms : outcome, effect, impacts

## Slide 4: What is RBM?
Definition (Organization for Economic Co-operation and Development: OECD 2002):
  ”RBM is a management strategy focusing on performance and achievement of outputs, outcomes and impacts.” Related term: logical framework
Definition (CIDA 2000)
  “RBM is a management philosophy and approach that emphasizes development of results in planning, implementation, learning and reporting.”

## Slide 5: RBM and changes
Sphere of control = operational environment
Direct control
Programme/
projects
Sphere of influence = relationships & interactions
Direct influence
Actor groups/ Boundary partners
Sphere of interest
= social, economical, environmental factors
Indirect influence / Contribution
Stakeholders / beneficiaries
Inputs
Activities
Outputs
Outcomes /
result areas
Impacts

## Slide 6: The RBM approach
LFA/GOPP
Monitoring systems:
-In the field
-Auto-monitoring (internal reflection)
Management
Change management, adaptive management
OM

## Slide 7: RBM – Results: the change as starting point
Purpose
What is to be different?
Baseline
Where are we?
Notes: E
Start ----------------x---- instead of x-------------------- What results/effect do we want our project to have instead of ”we have these resources and want to do these activities, where can we go?”
Monitor during the whole process in order to get the result we want.

## Slide 8: RBM
Define expected results
Focus attention on result achievement
Measure performance regularly and objectively
Learn from performance information
Make adjustments
Improve the efficiency and effectiveness

## Slide 9: Results chain (OECD)
Input Activity Output Outcome Impact
The Intervention (input to output, sphere of control)
Result (output to impact, sphere of influence)
Effects of the intervention (outcome to impact, sphere
of influence)

## Slide 10: Chain of Results
Input
Activity
Output
Outcome
Impact
The time and resources being invested in a project
The activities implemented, operations
The ”product” / service the activities create (e.g. Increased knowledge)
The changes of behavior in the target group as a result of the output
More long term (structural) changes created due to the outcomes (i.e. What will outlive the project)

## Slide 11: RBM Terminology
Input: The human, financial or material resources used.
Activity: Actions to be undertaken within the scope of the project. Ex. Training
Output: Positive/negative, primary/secondary, intended/ un-intended short-term results and effects of
completed activities. Ex. New skill or ability that resulted from the training
Outcome: Short and medium-term results and effects. Ex. Change of attitude/change on organizational level
Impact: Long-term results and effects.
Ex. Change on institutional or national level
Notes: E
Start with outcome!

## Slide 12: Chain of Results
Input
Activity
Output
Outcome
Impact
The financial, human and material resources used for the intervention
The ”product” / service the activities create (e.g. Increased knowledge)
The likely or achieved short ­ term and medium­ term effects of the intervention
Positive and negative, primary
and secondary long­
term effects produced by the intervention based on the expected
outcomes
RESULTS
Actions taken or work performed to produce
The intervention
The effects

## Slide 13: One chain, several chains?
From input to output.
From outputs to outcome
Aggregations process: programme approach, networks, regionals interventions: Programme frame /operative independent projects or interventions

## Slide 14: Cause and effect relationship of results
Notes: E

## Slide 16: RBM approach

## Slide 17: Follow-up of results
1. Chain of results (Output-outcome-impact)
2. Results (by whom and for whom?) Local partners – cooperation partners – Sida – FD
3. Aggregating results: projects, organizations programs, national programs
4. The flexible approach
5. The learning process

## Slide 18
IMPACT
OUTCOME
INPUT
ACTIVITY
OUTPUT
RESULTS
FD / Sida
Sida’s
Partners
Local partners
INTERVENTION

## Slide 19: Steps in creating a result oriented organization
RBM presents a modern concept for creating a result oriented organization
(OECD/DAC) presents 7 steps for establishing a result based culture according to RBM
These steps describe a sequence going from planning, implementing, follow-up, evaluation and management

## Slide 20: 3 dimensions, 7 steps
    1. Planning
        Formulation of goals
        Formulation of results
        Identification of indicators
    2. Implementation
        Follow-up of results
        Reporting of results
    3. Result based leadership (management)
        Integration of recommendations from evaluations
        Using information generated by implementation

## Slide 21: Planning (strategic)
Formulation of strategic goals
In order to apply RBM there has to be goals formulated: Present the expected future image of reality that can be affected by the organization/project.
Formulating results/effects: Outcomes and outputs?
Identification of indicators: tools to measure results and make necessary decisions through analysis of relevant information, make adjustments and align with the set strategic direction.

## Slide 22: …Planning (strategic)
Risk management
Risk management is a part of RBM
Risks must be identified and followed up
Potential internal risks – related to input and the activities output
External: affects the relationship output-outcome-impact

## Slide 23: Planning (operative)
Activities
Resources